## All Sites
Sites | Integration date | issues | pending | RFS
DXB-1963-IBS-SAR-M-1 |  |  |  | done
DXB-2041-IBS-SAR-M-1 |  |  |  | done |  |  | HO email sent | Sent to Hrishikish for rfs
FUJ-0620-IBS-SAR-M-1 |  |  |  | done |  |  | RFS done | It is rfs’d and in service by du
IDX-5057-IBS-SAR-M-1 |  |  |  | done
DXB-2632-IBS-SAR-M-1 |  |  |  | done
DXB-0217-IBS-SAR-M-1 |  |  |  | done
DXB-0958-IBS-SAR-M-1 |  |  |  | done
IDX-5039-IBS-SAR-M-1 |  |  |  | PENDING | RISH SENT NOT RFS
UAQ-2922-IBS-SAR-M-1 |  |  |  | done
DXB-2944-IBS-SAR-M-1 |  |  |  | done
DXB-3171-IBS-SAR-M-1 |  |  |  | done
IDX-5042-IBS-SAR-M-1 |  |  |  | PENDING | RISH SENT NOT RFS
SHJ-2033-IBS-SAR-M-1 |  |  |  | done
DXB-0156-IBS-SAR-M-1 |  |  |  | done
DXB-0712-IBS-SAR-M-1 |  |  |  | done
DXB-1127-IBS-SAR-M-1 |  |  |  | done
DXB-0580-IBS-SAR-M-1 |  |  |  | done
DXB-0954-IBS-SAR-M-1 |  |  |  | done
RAK-0520-IBS-SAR-M-1 |  |  |  | done
IDX-5015-IBS-SAR-M-1 |  |  |  | done
DXB-0488-IBS-SAR-M-1 |  |  |  | done
DXB-0011-IBS-SAR-M-1 |  |  |  | done
FUJ-2108-IBS-SAR-M-1 |  |  |  | done
RAK-2732-IBS-SAR-M-1 | 2015-03-08 |  |  | done
DXB-1883-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0110-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0328-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0129-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0575-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0211-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0432-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0447-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0275-IBS-SAR-M-1 | 2015-03-09 |  |  | done
DXB-0316-IBS-SAR-M-1 | 2015-03-12 |  |  | HO email sent
DXB-0836-IBS-SAR-M-1 | 2015-03-13 |  |  | done
DXB-1313-IBS-SAR-M-1 | 2015-03-13 |  |  | done
DXB-1397-IBS-SAR-M-1 | 2015-03-13 |  |  | done
DXB-0500-IBS-SAR-M-1 | 2015-03-13 |  |  | done
IDX-5034-IBS-SAR-M-1 | 2015-03-13 |  |  | done
DXB-0367-IBS-SAR-M-1 | 1900-03-16 |  |  | done
AUH-0409-IBS-SAR-M-1 | 17March FM 18 |  |  | HO email sent
DXB-0203-IBS-SAR-M-1 | 17March FM 18 |  |  | HO email sent
SHJ-2508-IBS-SAR-M-1 | 2015-03-19 |  | EVY THING done | HO email sent
DXB-0582-IBS-SAR-M-1 | 2015-03-19 |  | EVY THING done | HO email sent
AUH-2412-IBS-SAR-M-1 | 2015-03-19 |  | EVY THING done | HO email sent
DXB-2907-IBS-SAR-M-1 | 2015-03-19 |  | AMR STOPS FROM HO;Roll out for this site is in this above 3 package |  | AMR STOPS THE HO DUE TO VIRTUAL LOCALITY | IT IS IN 19 MARCH HV TO CREATE NEW HO DOC AND IT IS IN DU SHARED DRIVE
DXB-2992-IBS-SAR-M-1 | 2015-03-22 |  | HV TO HO
DXB-0927-IBS-SAR-M-1 | 2015-03-22 |  | HV TO HO
DXB-0764-IBS-SAR-M-1 | 2015-03-22 |  | HV TO HO
DXB-0261-IBS-SAR-M-1 | 2015-03-18 | PENDING | BDS SITES, AKRAM STOPS FROM FM
DXB-0749-IBS-SAR-M-1 | 2015-03-18 | PENDING | BDS SITES, AKRAM STOPS FROM FM
SHJ-0191-IBS-SAR-M-1 | 2015-03-22 | PENDING | No coordinates

## Record
DXB-0273-IBS-SAR-M-1 | 2015-03-09 | NOT IN RECORD | NOT Integrated

## ESSA SITES THIS WEEK
CSR Site ID | IIB HUB | Integrated | Zone
DXB0316 | DXB3215 | 2015-03-11 | In
DXB1515 | DXB-THEVILLA-POP-ME49-BDS-3A | 2015-03-16 | Out
DXB0203 | DXB1003 | 2015-03-17 | In
AUH0409 | AUH-MariaIsland-PREAGG-SR7-1 | 2015-03-17 | Out
AUH2412 | AUH2392 | 2015-03-18 | Out
DXB0261 |  | 2015-03-18 | Out
DXB0749 |  | 2015-03-18 | Out
SHJ2508 | SHJ-2053 | 2015-03-19 | Out
DXB0582 | DXB3252 | 2015-03-19 | In
SHJ0191 | SHJ-2049-PREAGG-SR7-1 | 2015-03-19 | Out
DXB2992 | DXB6020 | 2015-03-19 | In
DXB2907 | DXB1003 | 2015-03-21 | In
DXB0927 | DXB-Business Bay | 2015-03-21 | In
DXB0764 | DXB-3155-PREAGG-SR7-1 | 2015-03-21 | In